## KODU GOALS M2
KODU | Milestone 2 (18-Jun-12 - 22-Jun-12) | PRIORITY | OWNER | DUE
Get all elements to Alpha (less Level 4)
| ROVER MODEL/TEXTURE & In Game | 1
| Model and Texture Rover (2 LODs) | 1 | Tamas | LOD post Alpha
| Modeling and Texturing - Code Support | 1 | Dave M | Done
| Animate Rover | 1 | Tamas | Done
| Animation - Code Support | 1 | Dave M | Done
| Realistic wheel physics - Code Support | 3 | Dave M | Post Alpha
| Realistic wheel physics - Animation & Rig | 3 | Tamas | Post Alpha
| Rover SFX - Creation | 1 | Cam | Thursday
| Rover SFX - Integration | 1 | Dave M | Friday - 2 only
ROCK TYPES MODEL TEXTURE & In Game
| Model and Texture Rocks (3 Rocks, 2 LODs each) | 1 | Tamas | LOD post Alpha
| Modeling and Texturing - Code Support | 1 | Dave M | Done
| LEVEL 1 to ALPHA | 1
| Bring Level 1 to First draft | 1 | Martin | Done
| Level 1 first draft Review | 1 | All | Done
| Bring Level 1 to ALPHA | 1 | Martin | Friday
| LEVEL 2 to ALPHA | 2
| Bring Level 2 to First draft | 2 | David D | Done
| Level 2 first draft Review | 2 | All | Done
| Bring Level 2 to ALPHA | 2 | David D | Friday
| Review Curiculum and provide Feedback | 1 | Design | Done
| LEVEL 3 | 2
| Refine Level 3 Design based on Feedback | 2 | Martin | Done
| Get Signoff from MS on new Designs | 2 | Martin | Done
| Bring Level 3 to First draft | 2 | Martin | Thursday
| Level 3 first draft Review | 2 | All | Thursday
| Bring Level 3 to ALPHA | 2 | Martin | Friday
| Review Curiculum and provide Feedback | 1 | Design | Done
| LEVEL 4 to ALPHA (Stretch Goal) | 3
| Bring Level 4 to First draft | 3 | David D | Friday
| Review Curiculum and provide Feedback | 1 | Design | Done
| Tile 1 (Inspect) In Game | 1
| Spec/Grammar doc | 1 | Martin | Done
| Actuator task | 1 | Steve | Done
| Sensor task | 1 | Steve | Done
| Tile icon (1st Pass) | 1 | Tamas | Friday
| Tile Effect (Placeholder) | 1 | Tamas | Friday
| Tile Effect - Code support | 1 | Steve | Friday
| Audio SFX - Creation | 1 | Cam | Friday
| Audio SFX - Integration | 1 | Steve | Friday - 1 only
| Tile 2 (Beam) In Game | 1
| Spec/Grammar doc | 1 | Martin | Done
| Actuator task | 1 | Steve | Done
| Sensor task | 1 | Steve | Done
| Tile icon (1st Pass) | 1 | Tamas | Friday
| Tile Effects (Beam & Smoke) (Placeholder) | 1 | Tamas | Friday?
| Tile Effect - Code support | 1 | Dave M | Friday?
| Audio SFX - Creation | 1 | Cam | Friday
| Audio SFX - Integration | 1 | Steve | Friday - 1 only
| Tile 3 (Photography) In Game | 3
| Spec/Grammar doc | 3 | Martin | Done
| Actuator task | 3 | Dave M | Done
| Tile icon (1st Pass) | 3 | Tamas | Friday
| Tile Effect (Placeholder) | 3 | Tamas | Friday?
| Tile Effect - Code support | 3 | Dave M | Friday?
| Audio SFX - Creation | 3 | Cam | Friday
| Audio SFX - Integration | 3 | Steve | Friday - 1 only
| Tile 4 (Scan) In Game | 1
| Spec/Grammar doc | 1 | Martin | Done
| Actuator task | 1 | Dave M | Done
| Tile icon (1st Pass) | 1 | Tamas | Friday
| Tile Effect (Placeholder) | 1 | Tamas | Friday?
| Tile Effect - Code support | 1 | Dave M | Friday?
| Audio SFX - Creation | 1 | Cam | Friday
| Audio SFX - Integration | 1 | Steve | Friday - 1 only
| Rock type Filter Tile In Game | 1
| Spec/Grammar doc | 1 | Martin | Done
| Beam integration | 1 | Steve | Done
| Inspect integration | 1 | Steve | Done
| Rover Object support | 1 | Dave M | Done
| Rock Object support | 2 | Dave M | Partial
| Tile icon (Placeholder) | 1 | Tamas | Friday
| End of Path Tile In Game | 3
| Code implementation | 3 | Steve | Post Alpha
| Tile icon (Placeholder) | 3 | Tamas | Post Alpha

## KODU GOALS M3
KODU | Milestone 3 (25-Jun-12 - 29-Jun-12) | PRIORITY | OWNER | DUE
Get all elements to Shippable (Code & Content Complete)
ROVER Refinements
| Model and Texture Rover LODs | 1 | Tamas
| Add extra animations (Entertainment, ???) | 2 | Tamas
| Properly scale Rover | 1 | Tamas
| Realistic wheel physics - Code Support | 3 | Dave M | Stretch
| Realistic wheel physics - Animation & Rig | 3 | Tamas | Stretch
| Rover SFX - Integrate all | 1 | Dave M
| Rover properly on ground | 1 | Dave M | Done
| Filter all Rover-specific tiles to only apply to Rover items | 1 | Steve
| Add duration to Actions (eg. Delay to Scan) - Code | 2 | Dave M
| Add duration to Actions (eg. Delay to Scan) - VFX | 2 | Tamas
| Implement FOV | 3 | Dave M
| Make Dirt Maps work | 2 | Dave M | Bug?
ROCK TYPES refinements
| Model and Texture Rocks LODs | 1 | Tamas
| Make Dirt Maps work | 2 | Dave M | Bug?
LEVEL 1 to Shippable
| Determine location/placement | 1
LEVEL 2 to Shippable
| Determine location/placement | 1
LEVEL 3 to Shippable
| Determine location/placement | 1
LEVEL 4 to Shippable
| Add map templates | 1
| Determine location/placement | 1
Tile 1 (Inspect) to Shippable
| Tile Effects (Final) | 1 | Tamas
| SFX - Integrate all | 1 | Dave M
| Tile icon (Final) | 3 | Tamas | Stretch
Tile 2 (Beam) to Shippable
| Tile Effects (Beam & Smoke) (Final) | 1 | Tamas
| Tile Effects (Beam & Smoke) - Shader Code Support | 2 | Dave M
| SFX - Integrate all | 1 | Dave M
| Tile icon (Final) | 3 | Tamas | Stretch
Tile 3 (Photography) to Shippable
| SFX - Integrate all | 1 | Dave M
| Tile icon (Final) | 3 | Tamas | Stretch
Tile 4 (Scan) to Shippable
| Tile Effects (Final) | 1 | Tamas
| Tile icon (Final) | 3 | Tamas | Stretch
| SFX - Integrate all | 1 | Dave M
Rock type Filter Tile In Game
End of Path Tile In Game
| Code implementation | 1 | Steve
| Tile icon (Final) | 1 | Tamas