## KOD GOALS M2 - W1
KODW M2 | WEEK 1 (26-Nov-12 - 30-Nov-12) | ESTIMATE | OWNER | STATUS
PRIORITY | TOWER DEFENSE GAMEPLAY
GOAL:
| Level Style established |  | Martin | Done
| Camera solidified (Angle, Distance, etc.) |  | Martin | Done
| Fans, Currents, Paths prototyped |  | Martin | Done
| Basic touch working |  | Dave M. | To W2
CHARACTERS
GOAL: Visual Designs for all Characters and Objects completed
| Fan Particle Visualization concepts completed |  | Tamas | Done
| Placeholders for all Characters and Objects integrated |  | Tamas | To W2
| Starfish Placeholder integrated |  | Tamas | To W2
| Octopus Placeholder integrated |  | Tamas | Done
| Octopus Ink placeholder effect implemented |  | Tamas | Done
| Clam Placeholder integrated |  | Tamas | To W2
| Seagrass Placeholder integrated |  | Tamas | To W2
| Kelp Placeholder integrated |  | Tamas | To W2
WATER
GOAL: Initial functionality working
| Initial Fan implemented and Currents working |  | Eric | Done
| Octopus Gameplay tile (Ink) implemented (1/2) |  | Eric | Done
| Octopus Gameplay tile (Camouflage) implemented (1/2) |  | Eric | Done
WINDOWS 8 TOUCH
GOAL:
| Basic Touch Tile implementation working |  | Dave M. | Done
| First pass touch-based menus working |  | Dave M. | Done
LINKED LEVELS
GOAL: None this Week
DLC
GOAL: All open questions answered
| Need Steam Developer Account |  | Tim | To W2
| Need Windows Marketplace Developer Account |  | Tim | To W2
TELEMETRY
GOAL: None this Week
AUDIO
GOAL: None this Week
OTHER
GOAL: All open questions answered by MS
| Telemetry - What to track, which Client to integrate, support needed from Server team |  | Tim | To W2
| Hardware - ETA for more Touch Hardware |  | Tim | To W2

## KOD GOALS M2 - W2
KODW M2 | WEEK 2 (03-Dec-12 - 07-Dec-12) | ESTIMATE | OWNER | STATUS
PRIORITY | TOWER DEFENSE GAMEPLAY |  |  |  | Tamas OOO 07-Dec-12
GOAL:
| Basic Game rules and conditions working |  | Martin
| Prototype Object functionality working |  | Martin
| Basic touch working |  | Dave M. | From W1
CHARACTERS
GOAL: Visual Designs for all Characters and Objects signed off by MS
GOAL: Placeholders for all Characters and Objects integrated
| Finish Fan object (Modeling & Texturing) |  | Tamas
| Finish Octopus (Modeling & Texturing) |  | Tamas
| Start Octopus Animations |  | John H.
| Finish Clam (Modeling & Texturing) (Stretch) |  | Tamas
| Starfish Placeholder integrated |  | Tamas | From W1
| Clam Placeholder integrated |  | Tamas | From W1
| Seagrass Placeholder integrated |  | Tamas | From W1
| Kelp Placeholder integrated |  | Tamas | From W1
WATER
GOAL: All new Characters & Objects implemented (First Pass)
| Octopus Gameplay tile (Ink) implemented (2/2) |  | Eric
| Octopus Gameplay tile (Camouflage) implemented (2/2) |  | Eric
| Starfish Gameplay tile implemented |  | Eric
| Clam Gameplay tile implemented (with Open/Close support) |  | Eric
| Seagrass Gameplay tile implemented (with 'Sway' idle support) |  | Eric
| Kelp Gameplay tile implemented (with 'Float' idle support) |  | Eric
WINDOWS 8 TOUCH
GOAL:
| More touch-based menus implemented |  | Dave M.
| Touch bug fixes & Design support |  | Dave M.
| New GUI Touch work (1/2) |  | Dave M.
LINKED LEVELS
GOAL: None this Week
DLC
GOAL: None this Week
| Need Steam Developer Account |  | Tim | From W1
| Need Windows Marketplace Developer Account |  | Tim | From W1
TELEMETRY
GOAL: None this Week
AUDIO
GOAL: None this Week
OTHER
GOAL: None this Week
| Telemetry - What to track, which Client to integrate, support needed from Server team |  | Tim | From W1
| Hardware - ETA for more Touch Hardware |  | Tim | From W1

## KOD GOALS M2 - W3
KODW M2 | WEEK 3 (10-Dec-12 - 14-Dec-12) | ESTIMATE | OWNER | STATUS
PRIORITY | TOWER DEFENSE GAMEPLAY |  |  |  | Tamas OOO All Week
| GOAL: 1 Level at Prototype Experience |  |  |  | Tim OOO 14-Dec-12
| 1 Level at Prototype Experience |  | Martin
| All Paper Designs complete |  | Martin
| All Text instances identified and Placeholder text in place |  | Martin
| Text asset planning completed |  | Martin
CHARACTERS
GOAL: Visual Art Direction for in-game objects completed and approved
GOAL: Character & asset designs are comped & proto-typed
GOAL: Proto-type of Kodu assets working to understand new tile functionality
| Octopus model tweaks |  | Dave T. | To M3W2
| Octopus FX |  | Dave T. | To M3W2
| Finish Seagrass |  | Dave T. | To M3W2
| Finish Kelp |  | Dave T. | To M3W2
| Art planning completed |  | Angie/Tim
WATER
GOAL: Kodu-cup features proto-typed; Water experiences working at prototype level
| Octopus Gameplay tile (Invisibility) implemented |  | Eric
| "Jump" functionality added to existing Fish (Stretch) |  | Eric
WINDOWS 8 TOUCH
GOAL: Touch implementation working in-game
| New GUI Touch work (2/2) |  | Dave M.
LINKED LEVELS
GOAL: None this Week
DLC
GOAL: None this Week
TELEMETRY
GOAL: None this Week
AUDIO
GOAL: Sound Designs are scoped and prepared
| Audio asset planning completed |  | Cam
OTHER
GOAL: None this Week
| Milestone 1 Build and Materials delivered to MS |  | Tim