## Sheet1
FEATURE | PRI | CODE | ART | DESIGN | AUDIO | PRODUCTION | TOTAL | MILESTONE | CONFIDENCE | NOTES
Water - Simple | 1 | 18 | 2 | 5 | 0 | 0 | 25 |  | Medium
Current Generator | 1 | 2 | 6 | 3 | 0 | 0 | 11 |  | Medium | Builds on "Water - Simple"
Water - Gameplay (Tower Defense) | 1 | 10 | 39.5 | 23 | 5 | 0 | 77.5 |  | Medium
Telemetry | 1 | 3 | 0 | 0 | 0 | 0 | 3 |  | High | New Features only
DLC Support | 1 | 17 | 1 | 0 | 0 | 0 | 18 |  | Low
Windows 8 Integration | 1 | 3.5 | 1 | 0 | 0 | 0 | 4.5 |  | Medium
Windows 8 Touch Support - Basic | 1 | 14 | 4 | 2 | 0 | 0 | 20 |  | Medium
Windows 8 Touch Support - New GUI | 1 | 5 | 4 | 2 | 0 | 0 | 11 |  | Medium
Windows 8 Touch Support - Terrain Editing | 1 | 11 | 5 | 8 | 0 | 0 | 24 |  | Medium
Linked Levels - Simple | 1 | 7 | 0.5 | 1 | 0 | 0 | 8.5 |  | High
Linked Levels - Medium (plus Simple) | 1 | 2.5 | 0 | 0 | 0 | 0 | 2.5 |  | High | Builds on "Linked Levels - Simple"
Setup/Build Integration | 1 | 5 | 0 | 0 | 0 | 0 | 5 |  | High
Production Support | 1 | 0 | 0 | 0 | 0 | 36 | 36 |  | High
Bug Fixing | 1 | 10 | 5 | 5 | 0 | 5 | 25 |  | High
Total |  | 108 | 68 | 49 | 5 | 41 | 271